## Slide 1: Complex Project Scheduling Lessons Learned from NASA, Boeing, General Dynamics and Others
IEEE Aerospace Conference 2019
Rob Richards, Ph.D.
Stottler Henke Associates, Inc.

## Slide 2: LESSONS
Efficient scheduling is incredibly difficult
  Significant productivity lost due to inferior scheduling
Learn from the human schedulers
Model to level of detail required
Reveal & explain the schedule
Easy & fast to perform scenarios / what-ifs

## Slide 3: Efficient Scheduling Difficult
  Model to level of detail required
  Capture human reasoning
  Different scheduling applications generally require different algorithms

## Slide 4: Aurora’s scheduling process breakdown

## Slide 5: Scheduling results – refinery project

## Slide 6: MS Project results VS. Aurora-ksc results

## Slide 7: Learn from HUMAN SCHEDULERS
  When decisions / tradeoffs need to be made, use the expertise of expert schedulers
    So that the scheduling system reacts as a human expert wants it to
    E.g., when to work overtime, when to outsource
  Different scheduling applications generally require different algorithms
    Human experts help drive the best decision per algorithms

## Slide 8: USER SETTINGS

## Slide 9: MODEL TO level of detail required
Technical constraints (E.g., F-S, F-F, S-F, lags)
Resources
  Labor: Occupation, skills, certifications
  Equipment, Tools (e.g., cranes)
Usage constraints – e.g., tool can only be used for so many hours continuously &/or during a day.
Spatial / physical space – e.g.,
  job requires a certain location or type of space
  two elements should (or should not) be next to each other
Equipment substitutions – equipment down, know & use substitutes

## Slide 10: Concurrent CONSTRAINTS

## Slide 11: Non-concurrent CONSTRAINT

## Slide 12: NON-CONCURRENT constraints: red arrows

## Slide 13: Outsource AUTOMATION

## Slide 14: Remaining duration override

## Slide 15: Reveal and explain the schedule

## Slide 16: project network

## Slide 17: Gantt chart color-coded PER USER desired criteria

## Slide 18: Team assignment display

## Slide 19: Network diagram showing single-element view option

## Slide 20: Split view showing Gantt chart same time slice as histogram, showing activities constituting resource need for one time instance

## Slide 21: Vehicle testing schedule with build pitch

## Slide 22: Pharma Manufacturing Machine Utilization Report
Shows overall utilization of products by line
Allows planners to see overall allocation and line balancing

## Slide 23: Automatically generated explanation

## Slide 24: Easy & fast to perform scenarios / what-ifs
Wall clock minimization to run a scenario critical so schedulers will actually run them
Provide ways to graphically compare results

## Slide 25: What-If: Same Demand 3 vs 2 Lines

## Slide 26: What-if: Demand Increase

## Slide 27: What-if: WORK WEEKEND to GET BACK On Schedule

## Slide 28: LESSONS
Efficient scheduling is incredibly difficult
  Significant productivity lost due to inferior scheduling
Learn from the human schedulers
Model to level of detail required
Reveal & explain the schedule
Easy & fast to perform scenarios / what-ifs

## Slide 29: Aurora Available to all of NASA BOEING ALSO has site license